## Sheet1
S.No | Task No | Task Name | Task Descrption | Owner | Responsible | Target Date
1 | T-01 | Project Scaffolding & Dependencies | Initialize a new React project with Vite, install required packages ( axios , react-router-dom , lucide-react , react-icons , swiper ), and verify the dev server runs |  | Abdisa | 2026-10-30
2 | T-02 | Asset Organization & Static Data | Place image assets in src/assets/image/ (logo, fallback banner) and review src/Data/Data.js to understand the movie data structure |  | Abdisa | 2026-10-30
3 | T-03 | TMDB API Key & Environment Setup | Obtain a TMDB API key, configure it in .env as VITE_TMDB_API_KEY , and add .env to .gitignore . |  | Abdisa | 2026-10-30
4 | T-04 | Axios Instance & Request Endpoints | Create a shared Axios instance with the TMDB base URL in src/Utility/MovieInstance.js and define all category endpoint URLs in src/Utility/requestUrls.js |  | Abdisa | 2026-10-30
5 | T-05 | Global Theme & Base Styles | Set up the universal CSS reset and dark theme styling (black background and white text) in src/index.css . |  | Welde | 2026-11-01
6 | T-06 | App Layout Shell & Router | Wrap the application with in main.jsx and assemble the main layout component structure in App.jsx |  | Welde | 2026-11-01
7 | T-07 | Header & Scroll-Aware Background | Build a fixed header displaying the Netflix logo, primary navigation links, and a background that smoothly transitions from transparent to solid dark on page scroll. Design Reference: Resources/Designs/1.HeaderWithoutDropDown.png |  | Welde | 2026-11-01
8 | T-08 | Header Search, Notifications & Profile Dropdown | Add interactive header elements: an expandable search input toggle, a notification icon with badge, and a profile dropdown menu. Design Reference: Resources/Designs/2.HeaderWithSearchIconExpanded.png |  | Fikirte Molla | 2026-11-01
9 | T-09 | Responsive Footer Component | Description: Build the footer featuring social media icons, a multi-column links grid with hover states, and copyright info. Design Reference: Resources/Designs/6.Footer.png |  | Abdulkerim Seid | 2026-11-01
10 | T-10 | Banner Data Fetching & Random Selection | Fetch Netflix Originals from TMDB on component mount, randomly select one item to feature, and save it in state. |  | Semhal Habte | 2026-11-01
11 | T-11 | Banner UI & Gradient Overlay | Build the hero banner displaying the backdrop image, title, truncated description, "Play" and "My List" buttons, and a bottom fade gradient. Design Reference: Resources/Designs/4.BannerWithHeader.png |  | Nahom Fisseha | 2026-11-01
12 | T-12 | Multi-Category Parallel Fetching | Fetch movie lists for all genre categories concurrently using Promise.all in DisplayRow.jsx and store them in state |  | Wubgzer Alemayehu ,Abubeker Muhammed | 2026-11-01
13 | T-13 | SlideShow Swiper Carousel | Build a reusable Swiper carousel component with navigation arrows that appear on row hover. Design Reference: Resources/Designs/5.Row.png |  | Anwar Buta, Abomsa Kebede | 2026-11-01
14 | T-14 | MovieCard Component & Hover Preview | Build movie cards with poster thumbnails that expand on hover to show preview details, action buttons (play, add, like, more info), metadata tags, and genres. Design Reference: Resources/Designs/5HoverEffectOnCard.png |  | Biniyam Tesfaye | 2026-11-01
15 | T-15 | Responsive Layout & Mobile Navigation | Add media queries across header, banner, and movie rows to optimize spacing, typography, and element visibility on tablet and mobile viewports |  | Samrawit Worku | 2026-11-01
16 | T-16 | CSS Modules Audit & Animation Polish | Ensure scoped styling consistency across all CSS Module files, clean class naming, and smooth transition animations on all interactive components. |  |  | 2026-11-01